## Overview
Liminal Project Status Showcase
Windows + Unreal Engine 5.7 snapshot for the current repo-backed graybox build
Generated on 2026-05-10 ¦ Branch main ¦ Head 8b6486e ¦ Repo dirty
Build Phase |  |  |  | Git State |  |  | Overall Readiness
Graybox Visualization |  |  |  | main / dirty |  |  | 71%
Playable Maps |  |  |  | Blueprint Assets |  |  | UI Widgets
3 |  |  |  | 14 |  |  | 2
CSV Exports |  |  |  | Passing Tests |  |  | Validated Records
23 |  |  |  | 34 |  |  | 79
Workstream | Status | Completion % | What Exists | Current Constraint | Next Unlock
Windows + Repo Workflow | On track | 100 | Startup scripts, clean main pushes, Windows docs, UE launch path. | None | Keep status reporting current.
Unreal Project Shell | On track | 100 | Content-first UE5.7 project, startup map, game mode shell. | None | Preserve shell while wiring gameplay.
Graybox Maps | On track | 85 | Hub, personal room, and service halls layouts are live. | Needs gameplay beats inside spaces. | Add pacing and traversal moments.
Placeholder Actors + UI | On track | 80 | Core interaction anchors and HUD/result widgets exist. | Most are still static placeholders. | Wire interactions and states.
Data Pipeline | Working | 75 | 79 validated records and 23 exported Unreal CSVs. | Safe UE5.7 import path still blocked. | Use editor-authored structs for import.
Runtime Prototypes | Working | 70 | Inventory, board, persistence, and loop contracts are built. | Not bridged to Blueprints yet. | Bind contracts into Unreal-facing assets.
First Playable Loop | Needs work | 35 | Map route exists and core anchors are placed. | No full interactive run flow yet. | Connect deploy, loot, extract, deposit.
Atmosphere + Tuning | Needs work | 25 | Readability pass and signage are in the maps. | No mood, sound, or encounter tuning yet. | Layer tension and visual storytelling.
Current Snapshot | [5 empty] | Active Constraints
1. Windows-first, content-only Unreal project opens cleanly from LiminalDominion.uproject. | [5 empty] | 1. Automated CSV -> DataTable import is still blocked by a reproducible UE5.7 Python row-struct crash.
2. Three repo-owned graybox maps are in place: hub, personal room, and level 1 service halls. | [5 empty] | 2. Most placed Blueprint actors are still placeholders with limited or no gameplay logic wired in.
3. Deployment, loot, extraction, storage, board, trader, quartermaster, faction selector, and relic display anchors exist. | [5 empty] | 3. The first complete deploy -> loot -> extract -> deposit loop is not interactive in-editor yet.
4. Repo-side prototypes cover inventory, storage overflow, board upgrades, persistence, loadouts, and loop simulation. | [5 empty] | 4. Persistence and economy contracts exist in repo scripts but still need Unreal-side bridges.
5. GitHub main is synced through 8b6486e on 2026-05-10. | [5 empty] | 5. Atmosphere, tension, encounter pacing, and moment-to-moment readability still need a tuning pass.
6. Preflight, DataTable export, and the 34-test regression suite pass on Windows.

## Assets
Created Unreal Assets
Playable Maps
Map | Purpose | Current Notes
LD_Hub_Greybox | Startup hub and faction base shell | Contains deployment gate, project board, quartermaster, trader, and faction selector anchors.
LD_Level1_ServiceHalls_Greybox | First run graybox level | Contains loot, extraction, route signage, trader kiosk placeholder, and initial encounter space.
LD_PersonalRoom_Greybox | Personal room / stash space | Contains personal storage and relic display anchors for persistence-facing moments.
Blueprint Assets |  |  |  | UI Widgets
Blueprint | Category | Current Role | Status | Widget | Role | Status
BP_DeploymentGate | Interaction | Run deployment start point | Created | WBP_PlayerHUD | Placeholder HUD shell for the player loop. | Created
BP_ExtractionTrigger_HiddenTicketBooth | Interaction | Hidden extraction placeholder | Created | WBP_RunResult | Placeholder end-of-run summary screen. | Created
BP_ExtractionTrigger_Stable | Interaction | Primary stable extraction placeholder | Created
BP_FactionSelectorPlaceholder | Hub Placeholder | Faction choice anchor | Created
BP_FactionVaultPlaceholder | Hub Placeholder | Faction storage / vault anchor | Created
BP_FlickerStalker | Threat Placeholder | Enemy presence placeholder | Created
BP_LDGameMode | Framework | Project game mode shell | Created
BP_LDPlayer | Framework | Project player shell | Created
BP_LootContainer | Interaction | Loot source placeholder | Created
BP_PersonalStorage | Interaction | Persistent stash placeholder | Created
BP_ProjectBoard | Hub Interaction | Faction upgrade board anchor | Created
BP_QuartermasterPlaceholder | Hub Placeholder | Quartermaster anchor | Created
BP_RelicDisplayPlaceholder | Personal Room | Relic showcase anchor | Created
BP_TraderPlaceholder | Hub / Level Placeholder | Trader anchor | Created

## Systems
Systems and Pipeline Status
Area | Primary File | Type | What It Covers | Windows Verified | Unreal Bridge
Data Validation | scripts/validate_seed_data.py | Python | Validates seed data readability and schema compliance. | Yes | Indirect
Data Export | scripts/export_unreal_datatables.py | Python | Exports seed data into Unreal-ready CSV DataTables. | Yes | Indirect
Preflight | scripts/preflight_release.py | Python | Runs the end-to-end Windows verification pass. | Yes | Indirect
Inventory | scripts/inventory_model.py | Python | Handles caps, stack rules, and overflow behavior. | Yes | Pending
Project Board | scripts/project_board_model.py | Python | Handles faction contributions and upgrade completion. | Yes | Pending
Playable Loop | scripts/playable_loop_model.py | Python | Simulates deploy, loot, extract, and deposit outcomes. | Yes | Pending
Persistence | scripts/persistence_model.py | Python | Stores local profile, storage, and run history payloads. | Yes | Pending
Dev Check | scripts/check_dev_environment.py | Python | Verifies the Windows machine and Python launcher path. | Yes | Indirect
Unreal Launch | scripts/start_windows_unreal.ps1 | PowerShell | Opens the content-first UE project on Windows. | Yes | Direct
First Pass | scripts/unreal_first_pass_setup.py | Python | Creates the first placeholder content shell in Unreal. | Yes | Direct
Graybox Layout | scripts/unreal_graybox_layout.py | Python | Builds reusable map layout and signage passes. | Yes | Direct
Regression Tests | tests/test_data_tools.py | Python | Covers 34 runtime/data behaviors in the repo. | Yes | Indirect

## Data Exports
Exported Unreal DataTable CSVs
All 23 CSVs export successfully from the repo; manual Unreal import remains the current safe path.
Export | Rows | Purpose | Status | Notes
DT_Ammo | 2 | Ammo definitions and linkage. | Exported | Manual Unreal import still needed.
DT_Containers | 3 | Container rules and gate checks. | Exported | Manual Unreal import still needed.
DT_CraftingRecipes | 2 | Crafting recipe definitions. | Exported | Manual Unreal import still needed.
DT_Entities | 1 | Entity registry bootstrap definitions. | Exported | Manual Unreal import still needed.
DT_Extractions | 2 | Extraction rule definitions and requirements. | Exported | Manual Unreal import still needed.
DT_Factions | 3 | Faction identities and loadout rules. | Exported | Manual Unreal import still needed.
DT_HubUpgrades | 1 | Faction board upgrade definitions. | Exported | Manual Unreal import still needed.
DT_Items | 19 | Item registry and pickup metadata. | Exported | Manual Unreal import still needed.
DT_LevelLayouts | 1 | Level layout metadata and faction footholds. | Exported | Manual Unreal import still needed.
DT_LootDensity | 1 | Per-level loot density tuning. | Exported | Manual Unreal import still needed.
DT_LootTables | 4 | Loot distributions for level containers. | Exported | Manual Unreal import still needed.
DT_NPCRoster | 21 | Expanded NPC roster. | Exported | Manual Unreal import still needed.
DT_NPCs | 1 | Core NPC definitions. | Exported | Manual Unreal import still needed.
DT_NavigationMarkers | 1 | Navigation signage and breadcrumb markers. | Exported | Manual Unreal import still needed.
DT_NoiseResponses | 1 | AI / encounter response to noise events. | Exported | Manual Unreal import still needed.
DT_PlayerState | 1 | Player state defaults for prototypes. | Exported | Manual Unreal import still needed.
DT_Quests | 5 | Quest definitions and rewards. | Exported | Manual Unreal import still needed.
DT_RunState | 1 | Run state defaults for prototypes. | Exported | Manual Unreal import still needed.
DT_Sanity | 1 | Sanity values and recovery tuning. | Exported | Manual Unreal import still needed.
DT_SocialRules | 1 | Faction and social encounter rules. | Exported | Manual Unreal import still needed.
DT_Storage | 3 | Personal storage capacity rules. | Exported | Manual Unreal import still needed.
DT_Traders | 1 | Trader inventory and exchange definitions. | Exported | Manual Unreal import still needed.
DT_Weapons | 3 | Weapon definitions and behaviors. | Exported | Manual Unreal import still needed.

## Milestones
Recent Milestones
Date | Commit | Milestone | Impact
2026-05-10 | 8b6486e | Add Unreal objective readability pass | Added quartermaster, trader, faction selector, relic display, and route readability anchors.
2026-05-10 | ded35e0 | Build Unreal graybox shell layouts | Built the first reusable shell layout across hub, room, and service halls.
2026-05-07 | ed05e4d | Normalize Unreal input config | Stabilized editor input defaults for the content-only path.
2026-05-07 | 32ff938 | Add Unreal graybox placeholder assets | Created the first set of repo-owned Blueprint and UI placeholder assets.
2026-05-07 | a45534e | Add playable loop and local persistence prototypes | Added simulated loop, hub contribution, and save payload contracts.
2026-05-07 | 1626ba1 | Add storage overflow prototype and refresh Unreal docs | Completed stash overflow handling and aligned the docs to the Unreal path.
2026-05-06 | 861c074 | Add faction loadout and inventory weight prototypes | Added inventory capacity and faction loadout logic.
2026-05-01 | c674150 | Set up Windows Unreal visualization workflow | Established the Windows-first Unreal project workflow and startup path.

## Next Steps
Recommended Next Steps
Priority | Area | Action | Owner | Expected Unlock
P1 | Unreal Data | Create editor-authored row structs and manually import the 23 CSVs as DataTables. | Sean + Codex | Unblocks real Blueprint data binding.
P1 | Blueprint Wiring | Connect deployment gate, loot container, extraction trigger, personal storage, and project board to usable interactions. | Codex + Sean | Creates the first full in-editor loop.
P1 | Run Flow | Wire service halls to support deploy -> loot -> extract -> deposit with visible success/fail feedback. | Codex + Sean | Turns the graybox into a testable slice.
P2 | Hub Loop | Hook trader, quartermaster, faction selector, and relic display into simple placeholder UI flows. | Codex + Sean | Makes the hub feel like a real progression space.
P2 | Threat Layer | Add first encounter behavior and sanity feedback inside service halls. | Codex + Sean | Introduces tension beyond navigation.
P2 | Persistence Bridge | Connect personal room storage and run history to the persistence prototype contract. | Codex + Sean | Preserves progress between runs.
P3 | Atmosphere | Tune lighting, route readability, signage, and audio mood in the three graybox maps. | Sean + Codex | Improves clarity and feel before polish.
P3 | Playtest Pass | Run a full Windows Unreal walkthrough and capture blockers in the backlog. | Sean + Codex | Converts the current build into a concrete task list.